## Summary
|  |  | Smoke test | [6 empty] | Main flow test | [6 empty] | Regression test
| Plan Start Date | Plan Finish Date | Count of MTC | Planned | Automated | In-progress | Pending | Deferred | %Complete | Count of MTC | Planned | Automated | In-progress | Pending | Deferred | %Complete | Count of MTC | Planned | Automated | In-progress | Pending | Deferred | %Complete | Remarks
Account Establishment-CRM | 2016-12-27 | 2017-02-01 | 9 | 9 | 9 | 0 | 0 | 0 | 100% | 14 | 14 | 12 | 0 | 0 | 0 | 85.71% | 27 | 27 | 16 | 0 | 8 | 3 | 59.26% | Main Flow: - Awaiting feature from dev: 1 (scripting complete) - Script in progress: 1 Regression: - Awaiting feature from dev: 3 (scripting complete) - Scripting in progress: 4 - Deffered to Wave 6 : 2
Account Maintenance - CRM | 2016-01-03 | 2017-01-25 | 12 | 12 | 3 | 0 | 7 | 2 | 25% | 41 | 41 | 25 | 5 | 7 | 4 | 60.98% | 34 | 23 | 5 | 0 | 18 | 0 | 21.74%
Purchase_Order_Receive | 2016-12-27 | 2016-12-30 | 8 | 8 | 7 |  | 0 | 1 | 87.5% | 2 | 2 | 2 | 0 | 0 | 0 | 100% | 6 | 6 | 5 |  |  | 1 | 83.33% | Deffered: 2(POCR-006, 34: Will be automated on 23rd Jan 2017)
Box_CheckIn_CheckOut | 2017-01-02 | 2017-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 100% | 2 | 2 | 2 | 0 | 0 | 0 | 100%
Manual_Tag_Assignment | 2017-01-09 | 2017-01-13 | 2 | 2 | 2 | 0 |  | 1 | 100% | 2 | 2 | 2 | 0 | 0 | 0 | 100% | 2 | 2 | 2 | 0 | 0 | 0 | 100%
Inventory_Warranty_RMA _Program | 2017-01-18 | 2017-02-04 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 0 | 0

## Automation Status
Module | Procedure Name | Smoke Test Case ID | Main Flow Test Case ID | Regression Test Case ID | Planned for Automation | Assignee | No of PD's | Planned Start Date | Planned Finish Date | Automation Status | Outlook Completion Date | Comments
|  | 65 | 419 | 101 | 269
TPMS | LICA |  | LICA-001 |  | N | [6 empty] | 0
TPMS | LICA |  | LICA-005 |  | N
TPMS | LICA |  | LICA-007 |  | N
TPMS | LICA |  | LICA-008 |  | N
TPMS | LICA |  | LICA-026 |  | N
TPMS | LICA |  | LICA-092 |  | N
TPMS | LICA |  | LICA-093 |  | N
TPMS | LICA |  | LICA-052 |  | N
TPMS | LICA |  | LICA-094 |  | N
TPMS | LICA |  | LICA-065 |  | N
TPMS | LICA |  | LICA-095 |  | N
TPMS | LICA |  | LICA-068 |  | N
TPMS | LICA |  | LICA-076 |  | N
TPMS | LICA |  | LICA-078 |  | N
TPMS | LICA |  | LICA-085 |  | N
TPMS | LICA |  | LICA-086 |  | N
CAMS | Customer Statement |  | STMT-001 |  | N
CAMS | Customer Statement |  | STMT-003 |  | N
CAMS | Customer Statement |  | STMT-004 |  | N
CAMS | Customer Statement |  | STMT-005 |  | N
CAMS | Customer Statement |  | STMT-006 |  | N
CAMS | Customer Statement |  | STMT-018 |  | N
CAMS | Customer Statement |  | STMT-019 |  | N
CAMS | Customer Statement |  | STMT-021 |  | N
CAMS | Customer Statement |  | STMT-022 |  | N
CAMS | Customer Statement |  | STMT-044 |  | N
CAMS | Customer Statement |  | STMT-047 |  | N
CAMS | Customer Statement |  | STMT-054 |  | N
VEMS | Collection |  | VCOLL-001 |  | N
VEMS | Collection |  | VCOLL-001 |  | N
VEMS | Collection |  | VCOLL-002 |  | N
VEMS | Collection |  | VCOLL-005 |  | N
VEMS | Collection |  | VCOLL-006 |  | N
VEMS | Collection |  | VCOLL-016 |  | N
VEMS | Collection |  | VCOLL-030 |  | N
VEMS | Collection |  | VCOLL-032 |  | N
CAMS | CRM_Account_Maintenance | ACMO-004 | ACMO-004 |  | Y |  |  |  |  | Deferred |  | PIN update feature not availble on Siebel, requires discussion with Author
CAMS | CRM_Account_Maintenance |  | ACMO-008 |  | Y | Venkat | 1 | 2017-01-03 | 2017-01-03 | Completed
CAMS | CRM_Account_Maintenance |  | ACMO-0014 |  | Y | Sreeraj | 3 | 2017-01-05 | 2017-01-09 | Completed | 2017-01-09
CAMS | CRM_Account_Maintenance |  | ACMO-036 |  | Y |  |  |  |  | Deferred
CAMS | CRM_Account_Maintenance |  | ACMO-037 |  | Y | Laxmi | 2 | 2017-01-05 | 2017-01-06 | Completed
CAMS | CRM_Account_Maintenance | ACMO-038 | ACMO-038 |  | Y | Laxmi | 1 | 2017-01-09 | 2017-01-09 | Completed | 2017-01-09
CAMS | CRM_Account_Maintenance |  | ACMO-055 |  | Y | Laxmi | 2 | 2017-01-10 | 2017-01-11 | In-Progress
CAMS | CRM_Account_Maintenance |  | ACMO-075 |  | Y | Bharath | 2 | 2017-01-05 | 2017-01-06 | Completed | 2017-01-06
CAMS | CRM_Account_Maintenance |  | ACMO-076 |  | Y | Bharath | 1 | 2017-01-09 | 2017-01-09 | Completed | 2017-01-09
CAMS | CRM_Account_Maintenance |  | ACMO-077 |  | Y | Bharath | 1 | 2017-01-10 | 2017-01-10 | Completed | 2017-01-10
CAMS | CRM_Account_Maintenance |  | ACMO-078 |  | Y | Bharath | 0 | 2017-01-10 | 2017-01-10 | In-Progress
CAMS | CRM_Account_Maintenance |  | ACMO-079 |  | Y | Bharath | 0 | 2017-01-10 | 2017-01-10 | In-Progress
CAMS | CRM_Account_Maintenance |  | ACMO-085 |  | Y | Bharath | 1 | 2017-01-11 | 2017-01-11 | Completed | 2017-01-11
CAMS | CRM_Account_Maintenance |  | ACMO-088 |  | Y | Bharath | 1 | 2017-01-12 | 2017-01-12 | Completed | 2017-01-12
CAMS | CRM_Account_Maintenance |  | ACMO-089 |  | Y | Bharath | 0 | 2017-01-12 | 2017-01-12 | Completed | 2017-01-12
CAMS | CRM_Account_Maintenance |  | ACMO-108 |  | Y | Nishanth | 2 | 2017-01-06 | 2017-01-09 | Completed | 2017-01-09
CAMS | CRM_Account_Maintenance |  | ACMO-109 |  | Y | Nishanth | 1 | 2017-01-10 | 2017-01-10 | Completed | 2017-01-10
CAMS | CRM_Account_Maintenance |  | ACMO-110 |  | Y | Nishanth | 0 | 2017-01-10 | 2017-01-10 | Completed | 2017-01-10
CAMS | CRM_Account_Maintenance |  | ACMO-125 | ACMO-125 | Y | Laxmi | 2 | 2017-01-12 | 2017-01-13 | Completed | 2017-01-13
CAMS | CRM_Account_Maintenance |  | ACMO-131 |  | Y | Nishanth | 0 | 2017-01-10 | 2017-01-10 | Completed | 2017-01-10
CAMS | CRM_Account_Maintenance |  | ACMO-133 |  | Y | Nishanth | 0 | 2017-01-10 | 2017-01-10 | Completed | 2017-01-10
CAMS | CRM_Account_Maintenance |  | ACMO-138 |  | Y | Sreeraj | 2 | 2017-01-10 | 2017-01-11 | In-Progress
CAMS | CRM_Account_Maintenance |  | ACMO-139 |  | Y | Sreeraj | 0 | 2017-01-11 | 2017-01-11 | Planned
CAMS | CRM_Account_Maintenance |  | ACMO-141 |  | Y | Bharath | 1 | 2017-01-13 | 2017-01-13 | Planned
CAMS | CRM_Account_Maintenance |  | ACMO-143 |  | Y | Bharath | 0 | 2017-01-13 | 2017-01-13 | Planned
CAMS | CRM_Account_Maintenance |  | ACMO-180 | ACMO-180 | Y | Kavita | 2 | 2017-01-05 | 2017-01-06 | Completed | 2017-01-10
CAMS | CRM_Account_Maintenance |  | ACMO-181 |  | Y | Kavita | 0 | 2017-01-06 | 2017-01-06 | Completed | 2017-01-10
CAMS | CRM_Account_Maintenance |  | ACMO-193 |  | Y | Kavita | 2 | 2017-01-09 | 2017-01-10 | Completed | 2017-01-13
CAMS | CRM_Account_Maintenance |  | ACMO-196 |  | Y | Kavita | 1 | 2017-01-11 | 2017-01-11 | In-Progress
CAMS | CRM_Account_Maintenance |  | ACMO-199 |  | Y | Kavita | 1 | 2017-01-12 | 2017-01-12 | Planned
CAMS | CRM_Account_Maintenance |  | ACMO-200 |  | Y | Kavita | 0 | 2017-01-12 | 2017-01-12 | Planned
CAMS | CRM_Account_Maintenance |  | ACMO-205 |  | Y | Kavita | 0 | 2017-01-06 | 2017-01-06 | Completed | 2017-01-06
CAMS | CRM_Account_Maintenance |  | ACMO-206 |  | Y | Kavita | 0 | 2017-01-06 | 2017-01-06 | Completed | 2017-01-06
CAMS | CRM_Account_Maintenance |  | ACMO-207 |  | Y | Kavita | 0 | 2017-01-06 | 2017-01-06 | Completed | 2017-01-06
CAMS | CRM_Account_Maintenance | ACMO-215 | ACMO-215 |  | Y | Kavita | 1 | 2017-01-13 | 2017-01-13 | Completed | 2017-01-13
CAMS | CRM_Account_Maintenance |  | ACMO-216 |  | Y |  |  |  |  | Deferred
CAMS | CRM_Account_Maintenance | ACMO-219 | ACMO-219 |  | Y |  |  |  |  | Deferred |  | Requires discussion with Author on the expected result
CAMS | CRM_Account_Maintenance |  | ACMO-239 |  | Y | Nishanth | 1 | 2017-01-11 | 2017-01-11 | Completed | 2017-01-13
CAMS | CRM_Account_Maintenance |  | ACMO-240 |  | Y | Nishanth | 0 | 2017-01-11 | 2017-01-11 | Completed | 2017-01-13
CAMS | CRM_Account_Maintenance |  | ACMO-282 |  | Y | Nishanth | 1 | 2017-01-12 | 2017-01-12 | Planned
CAMS | CRM_Account_Maintenance |  | ACMO-296 |  | Y | Nishanth | 0 | 2017-01-12 | 2017-01-12 | Planned
CAMS | CRM_Account_Maintenance | ACMO-010 |  |  | Y | Boopathi | 1 | 2017-01-12 | 2017-01-12 | Completed | 2017-01-12 | Scripting part completed while executing this scenario found Defect Informed to Manual Team.
CAMS | CRM_Account_Maintenance | ACMO-057 |  |  | Y | Boopathi | 0 | 2017-01-12 | 2017-01-12
CAMS | CRM_Account_Maintenance | ACMO-082 |  |  | Y | Nishanth | 1 | 2017-01-13 | 2017-01-13 | Assigned
CAMS | CRM_Account_Maintenance | ACMO-100 |  |  | Y | Nishanth | 0 | 2017-01-13 | 2017-01-13 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-002 | Y | Boopathi | 1 | 2017-01-10 | 2017-01-10 | Completed | 2017-01-13
CAMS | CRM_Account_Maintenance |  |  | ACMO-062 | Y | Boopathi | 1 | 2017-01-11 | 2017-01-11 | Completed
CAMS | CRM_Account_Maintenance |  |  | ACMO-069 | Y | Boopathi | 0 | 2017-01-11 | 2017-01-11 | Completed
CAMS | CRM_Account_Maintenance | ACMO-107 |  | ACMO-107 |  | Sreeraj | 1 | 2017-01-16 | 2017-01-16 | Assigned
CAMS | CRM_Account_Maintenance | ACMO-285 |  |  | ACMO-285 | Sreeraj | 1 | 2017-01-17 | 2017-01-17 | Assigned
CAMS | CRM_Account_Maintenance | ACMO-235 |  |  | ACMO-235 | Sreeraj | 0 | 2017-01-16 | 2017-01-16 | Assigned
CAMS | CRM_Account_Maintenance | ACMO-265 |  |  | ACMO-265 | [6 empty] | Please validate the entry into t_mailhouse interface table as expected result
CAMS | CRM_Account_Maintenance |  |  | ACMO-175 |  | Sreeraj | 1 | 2017-01-18 | 2017-01-18 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-281 |  | Sreeraj | 1 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-295 |  | Sreeraj | 1 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-297 |  | Sreeraj | 0 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-282 |  | Sreeraj | 0 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-283 |  | Sreeraj | 0 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-284 |  | Sreeraj | 1 | 2017-01-20 | 2017-01-20 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-286 |  | Kavita | 1 | 2017-01-17 | 2017-01-17 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-287 |  | Kavita | 1 | 2017-01-18 | 2017-01-18 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-288 |  | Kavita | 0 | 2017-01-18 | 2017-01-18 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-289 |  | Kavita | 1 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-290 |  | Kavita | 0 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-291 |  | Kavita | 0 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-118 |  | Sreeraj | 1 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-201 |  | Kavita | 2 | 2017-01-20 | 2017-01-23 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-208 |  | Sreeraj | 2 | 2017-01-23 | 2017-01-24 | Assigned
CAMS | CRM_Account_Maintenance |  |  | ACMO-274 |  | Sreeraj | 1 | 2017-01-25 | 2017-01-25 | Assigned
CAMS | Account_Search |  | ACS-095 |  | Y | Boopathi | 1 | 2017-01-23 | 2017-01-23 | Assigned
CAMS | Account_Search |  | ACS-029 |  | Y | Boopathi | 0 | 2017-01-23 | 2017-01-23 | Assigned
CAMS | Account_Search |  | ACS-008 |  | Y | Boopathi | 0 | 2017-01-23 | 2017-01-23 | Assigned
CAMS | Account_Search |  | ACS-096 |  | Y | Boopathi | 0 | 2017-01-23 | 2017-01-23 | Assigned
CAMS | Account_Search | ACS-004 |  | ACS-004 |  | Boopathi | 1 | 2017-01-20 | 2017-01-20 | Assigned
CAMS | Account_Search | ACS-081 |  |  |  | Boopathi | 0 | 2017-01-20 | 2017-01-20 | Assigned
CAMS | Account_Search | ACS-060 |  |  |  | Boopathi | 0 | 2017-01-20 | 2017-01-20 | Assigned
CAMS | Account_Search | ACS-063 |  |  |  | Boopathi | 0 | 2017-01-20 | 2017-01-20 | Assigned
CAMS | Account_Search | ACS-087 |  |  |  | Boopathi | 0 | 2017-01-20 | 2017-01-20 | Assigned
CAMS | Account_Search | ACS-119 |  |  |  | Boopathi | 0 | 2017-01-20 | 2017-01-20 | Assigned
CAMS | Account_Search |  |  | ACS-003 |  | Boopathi | 2 | 2017-01-17 | 2017-01-18 | Assigned
CAMS | Account_Search |  |  | ACS-008 |  | Boopathi | 0 | 2017-01-18 | 2017-01-18 | Assigned
CAMS | Account_Search |  |  | ACS-025 |  | Boopathi | 0 | 2017-01-18 | 2017-01-18 | Assigned
CAMS | Account_Search |  |  | ACS-034 |  | Boopathi | 0 | 2017-01-18 | 2017-01-18 | Assigned
CAMS | Account_Search |  |  | ACS-035 |  | Boopathi | 0 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | Account_Search |  |  | ACS-086 |  | Boopathi | 1 | 2017-01-19 | 2017-01-19 | Assigned
WEB | Web_Account_Establishment | ACEW-005 | ACEW-005 | ACEW-005 | Y
WEB | Web_Account_Establishment |  | ACEW-001 | ACEW-001 | Y | [6 empty] | Wave 5
WEB | Web_Account_Establishment | ACEW-007 | ACEW-007 | ACEW-007 | Y
WEB | Web_Account_Establishment |  | ACEW-036 |  | Y
WEB | Web_Account_Establishment |  | ACEW-012 | ACEW-012 | Y
WEB | Web_Account_Establishment |  | ACEW-053 | ACEW-053 | Y | [6 empty] | Wave 5
WEB | Web_Account_Establishment |  |  | ACEW-023
WEB | Web_Account_Establishment |  |  | ACEW-032 | [7 empty] | Wave 5
WEB | Web_Account_Establishment |  |  | ACEW-037 | [7 empty] | Wave 5
WEB | Web_Account_Establishment |  |  | ACEW-039 | [7 empty] | Wave 5
WEB | Web_Account_Establishment |  |  | ACEW-048
WEB | Web_Account_Establishment |  |  | ACEW-049
WEB | Web_Account_Establishment |  |  | ACEW-051
WEB | Web_Account_Establishment |  |  | ACEW-055
WEB | Web_Account_Establishment |  |  | ACEW-058
WEB | Web_Account_Establishment |  |  | ACEW-061
WEB | Web_Account_Establishment |  |  | ACEW-063
WEB | Web_Account_Establishment |  |  | ACEW-065
WEB | Web_Account_Establishment |  |  | ACEW-072
WEB | Web_Account_Establishment |  |  | ACEW-074
TPMS | Discount_Plan |  | DISCPL-001 |  | N
TPMS | Discount_Plan |  | DISCPL-004 |  | N
TPMS | Discount_Plan |  | DISCPL-010 |  | N
TPMS | Discount_Plan |  | DISCPL-019 |  | N
TPMS | Discount_Plan |  | DISCPL-029 |  | N
TPMS | Discount_Plan |  | DISCPL-036 |  | N
TPMS | Invoice_Disputes |  | INVD-001 |  | N
TPMS | Invoice_Disputes |  | INVD-003 |  | N
TPMS | Invoice_Disputes |  | INVD-009 |  | N
TPMS | Invoice_Disputes |  | INVD-006 |  | N
TPMS | Invoice_Disputes |  | INVD-024 |  | N
TPMS | Invoice_Disputes |  | INVD-034 |  | N
TPMS | Invoice_Disputes |  | INVD-043 |  | N
ADMIN | Display_Checklist |  | DISPCH-001 |  | Y
ADMIN | Display_Checklist |  | DISPCH-004 |  | Y
ADMIN | Display_Checklist |  | DISPCH-009 |  | Y
ADMIN | Display_Checklist |  | DISPCH-011 |  | Y
ADMIN | Display_Checklist |  | DISPCH-015 |  | Y
ADMIN | Display_Checklist |  | DISPCH-022 |  | Y
ADMIN | Display_Checklist |  | DISPCH-028 |  | Y
ADMIN | Display_Checklist |  | DISPCH-090 |  | Y
ADMIN | Display_Checklist |  | DISPCH-098 |  | Y
ADMIN | Display_Checklist |  | DISPCH-110 |  | Y
ADMIN | Display_Checklist |  | DISPCH-131 |  | Y
ADMIN | Display_Checklist |  | DISPCH-134 |  | Y
ADMIN | Display_Checklist |  | DISPCH-135 |  | Y
ADMIN | Display_Checklist |  | DISPCH-145 |  | Y
ADMIN | Display_Checklist |  | DISPCH-160 |  | Y
DIMS | Purchase_Order_Receive | POCR-005 | POCR-005 |  | Y |  |  | 2016-12-27 | 2016-12-30 | Completed | 2016-12-30
DIMS | Purchase_Order_Receive | POCR-041 | POCR-041 | POCR-041 | Y |  |  | 2016-12-27 | 2016-12-30 | Completed | 2016-12-30
DIMS | Purchase_Order_Receive | POCR-001 |  | POCR-001 | Y |  |  | 2016-12-27 | 2016-12-30 | Completed | 2016-12-30
DIMS | Purchase_Order_Receive | POCR-002 |  |  | Y |  |  | 2016-12-27 | 2016-12-30 | Completed | 2016-12-30
DIMS | Purchase_Order_Receive | POCR-003 |  | POCR-003 | Y |  |  | 2016-12-27 | 2016-12-30 | Completed | 2016-12-30
DIMS | Purchase_Order_Receive | POCR-004 |  | POCR-004 | Y |  |  | 2016-12-27 | 2016-12-30 | Completed | 2016-12-30
DIMS | Purchase_Order_Receive | POCR-006 |  | POCR-006 | Y |  |  |  |  | Deffered
DIMS | Purchase_Order_Receive | POCR-040 |  | POCR-040 | Y |  |  | 2016-12-27 | 2016-12-30 | Completed | 2016-12-30
|  |  |  | POCR-034 | [5 empty] | Planned | We got informed late about one functionality: (Box transfer of multiple boxes), After automating PO, we came to know this functionality from Gour. So we need 2 more days to automate this. Within 2 days, we can one more new functionality suggessted by Gour.(Packaging company).
DIMS | Box_CheckIn_CheckOut |  | CICO-001 | CICO-001 | Y |  |  | 2017-01-02 | 2017-01-05 | Completed | 2017-01-06
DIMS | Box_CheckIn_CheckOut |  | CICO-013 | CICO-013 | Y |  |  | 2017-01-02 | 2017-01-05 | Completed | 2017-01-06 | Completed. But for this functionality, we have dependency with "manual tag assignment". Once that is atuomated, just we can run this and close the task.
DIMS | Manual_Tag_Assignment | MTGA-026 | MTGA-026 | MTGA-026 | Y |  |  | 2017-01-09 | 2017-01-13 | Completed
DIMS | Manual_Tag_Assignment |  | MTGA-030 |  | Y |  |  | 2017-01-09 | 2017-01-13 | Completed
DIMS | Manual_Tag_Assignment | MTGA-028 |  | MTGA-028 |  |  |  | 2017-01-09 | 2017-01-13 | Completed
DIMS | Batch_Tag_Assignment |  | BTGA-007 |  | Y
DIMS | Batch_Tag_Assignment |  | BTGA-016 |  | Y
DIMS | Batch_Tag_Assignment |  | BTGA-028 |  | Y
DIMS | Batch_Tag_Assignment |  |  | BTGA-002
DIMS | Batch_Tag_Assignment |  |  | BTGA-003
DIMS | Batch_Tag_Assignment | BTGA-009 |  | BTGA-009
TPMS | Quarterly_Evaluation |  | QEVAL-013 |  | N
TPMS | Quarterly_Evaluation |  | QEVAL-019 |  | N
TPMS | Quarterly_Evaluation |  | QEVAL-025 |  | N
VEMS | ROV_Account_Creation |  | ROVAC-003 |  | N
VEMS | ROV_Account_Creation |  | ROVAC-030 |  | N
VEMS | ROV_Account_Creation |  | ROVAC-037 |  | N
TPMS | QATP |  | QATP-001 |  | N
TPMS | QATP |  | QATP-139 |  | N
TPMS | QATP |  | QATP-069 |  | N
TPMS | QATP |  | QATP-163 |  | N
TPMS | QATP |  | QATP-166 |  | N
TPMS | QATP |  | QATP-210 |  | N
TPMS | QATP |  | QATP-211 |  | N
TPMS | QATP |  | QATP-222 |  | N
TPMS | QATP |  | QATP-223 |  | N
TPMS | QATP |  | QATP-225 |  | N
TPMS | QATP |  | QATP-231 |  | N
TPMS | QATP |  | QATP-249 |  | N
TPMS | QATP |  | QATP-276 |  | N
TPMS | QATP |  | QATP-294 |  | N
TPMS | QATP |  | QATP-332 |  | N
TPMS | Fleet |  | FAC-001 |  | N
TPMS | Fleet |  | FAC-022 |  | N
TPMS | Fleet |  | FAC-023 |  | N
TPMS | Fleet |  | FAC-024 |  | N
TPMS | Fleet |  | FAC-027 |  | N
TPMS | Fleet |  | FAC-048 |  | N
TPMS | Fleet |  | FAC-049 |  | N
TPMS | Fleet |  | FAC-050 |  | N
CASE | Case Management | CMGT-011 | CMGT-011 |  | Y | [7 empty] | Shaik, Asifa A
CASE | Case Management | CMGT-128 | CMGT-128 | CMGT-128 | Y
CASE | Case Management | CMGT-018 | CMGT-018 |  | Y
CASE | Case Management |  | CMGT-023 |  | Y
CASE | Case Management |  | CMGT-033 |  | Y
CASE | Case Management |  | CMGT-036 |  | Y
CASE | Case Management |  | CMGT-044 |  | Y
CASE | Case Management |  | CMGT-056 |  | Y
CASE | Case Management |  | CMGT-059 |  | Y
CASE | Case Management |  | CMGT-150 |  | Y
CASE | Case Management |  | CMGT-136 |  | Y
CASE | Case Management |  | CMGT-156 &CMGT-157 |  | Y
CASE | Case Management |  | CMGT-084 |  | Y
CASE | Case Management |  | CMGT-099 |  | Y
CASE | Case Management |  | CMGT-006 |  | Y
CASE | Case Management |  | CMGT-005 |  | Y
CASE | Case Management |  | CMGT-017 |  | Y
CASE | Case Management |  | CMGT-051 |  | Y
CASE | Case Management |  | CMGT-135 |  | Y
CASE | Case Management |  | CMGT-080 |  | Y
CASE | Case Management |  | CMGT-107 |  | Y
CASE | Case Management |  | CMGT-108 |  | Y
CASE | Case Management |  | CMGT-109 |  | Y
CASE | Case Management |  | CMGT-151 |  | Y
CASE | Case Management | CMGT-021
CASE | Case Management |  |  | CMGT-127
DIMS | Device Status Change |  | DEVST-001 |  | Y
DIMS | Device Status Change |  | DEVST-005 |  | Y
DIMS | Device Status Change |  | DEVST-010 |  | Y
DIMS | Device Status Change |  | DEVST-030 |  | Y
DIMS | Device Status Change |  | DEVST-037 |  | Y
DIMS | Device Status Change |  | DEVST-039 |  | Y
DIMS | Device Status Change |  | DEVST-044 |  | Y
RETAILER | Retailer Management |  | OTGO-001 |  | Y
RETAILER | Retailer Management |  | OTGO-065 |  | Y
RETAILER | Retailer Management |  | OTGO-015 |  | Y
RETAILER | Retailer Management |  | OTGO-020 |  | Y
RETAILER | Retailer Management |  | OTGO-022 |  | Y
RETAILER | Retailer Management |  | OTGO-034 |  | Y
RETAILER | Retailer Management |  | OTGO-036 |  | Y
RETAILER | Retailer Management |  | OTGO-038 |  | Y
RETAILER | Retailer Management |  | OTGO-040 |  | Y
RETAILER | Retailer Management |  | OTGO-070 |  | Y
RETAILER | Retailer Management |  | OTGO-077 |  | Y
VEMS | DMV Processing |  | DMV-001 |  | N
VEMS | DMV Processing |  | DMV-004 |  | N
VEMS | DMV Processing |  | DMV-008 |  | N
VEMS | DMV Processing |  | DMV-016 |  | N
VEMS | DMV Processing |  | DMV-017 |  | N
VEMS | DMV Processing |  | DMV-021 |  | N
VEMS | DMV Processing |  | DMV-023 |  | N
VEMS | DMV Processing |  | DMV-025 |  | N
VEMS | DMV Processing |  | DMV-027 |  | N
VEMS | DMV Processing |  | DMV-029 |  | N
VEMS | DMV Processing |  | DMV-038 |  | N
TPMS | Skip Tracing |  | SKIPT-002 |  | N
TPMS | Skip Tracing |  | SKIPT-007 |  | N
TPMS | Skip Tracing |  | SKIPT-009 |  | N
TPMS | Skip Tracing |  | SKIPT-019 |  | N
TPMS | Skip Tracing |  | SKIPT-022 |  | N
TPMS | Lockbox Payment Dispute |  | CYS-002 |  | N
TPMS | Lockbox Payment Dispute |  | CYS-003 |  | N
TPMS | Lockbox Payment Dispute |  | CYS-007 |  | N
TPMS | Lockbox Payment Dispute |  | CYS-012 |  | N
TPMS | Lockbox Payment Dispute |  | CYS-005 |  | N
TPMS | CC Expiration |  | CCEX-002 |  | N
TPMS | CC Expiration |  | CCEX-004 |  | N
TPMS | CC Expiration |  | CCEX-007 |  | N
TPMS | CC Expiration |  | CCEX-016 |  | N
TPMS | CC Expiration |  | CCEX-023 |  | N
TPMS | Rebill Processing |  | CCRB-001 |  | N
TPMS | Rebill Processing |  | CCRB-003 |  | N
TPMS | Rebill Processing |  | CCRB-013 |  | N
TPMS | Rebill Processing |  | CCRB-015 |  | N
TPMS | Rebill Processing |  | CCRB-017 |  | N
VEMS | DMV Registration Hold Release |  | DMVHLD-001 |  | N
VEMS | DMV Registration Hold Release |  | DMVHLD-002 |  | N
VEMS | DMV Registration Hold Release |  | DMVHLD-004 |  | N
VEMS | DMV Registration Hold Release |  | DMVHLD-006 |  | N
VEMS | DMV Registration Hold Release |  | DMVHLD-014 |  | N
VEMS | DMV Registration Hold Release |  | DMVHLD-016 |  | N
VEMS | DMV Registration Hold Release |  | DMVHLD-017 |  | N
VEMS | DMV Registration Hold Release |  | DMVHLD-020 |  | N
VEMS | LICA |  | LICA-001 |  | N
VEMS | LICA |  | LICA-005 |  | N
VEMS | LICA |  | LICA-007 |  | N
VEMS | LICA |  | LICA-008 |  | N
VEMS | LICA |  | LICA-026 |  | N
VEMS | LICA |  | LICA-092 |  | N
VEMS | LICA |  | LICA-093 |  | N
VEMS | LICA |  | LICA-052 |  | N
VEMS | LICA |  | LICA-094 |  | N
VEMS | LICA |  | LICA-065 |  | N
VEMS | LICA |  | LICA-095 |  | N
VEMS | LICA |  | LICA-068 |  | N
VEMS | LICA |  | LICA-076 |  | N
VEMS | LICA |  | LICA-078 |  | N
VEMS | LICA |  | LICA-085 |  | N
VEMS | LICA |  | LICA-086 |  | N
CAMS | Shift Management | SMGT-001 | SMGT-001 | SMGT-001 | Y | Harish | 1 | 2017-01-11 | 2017-01-11 | Completed | 2017-01-12
CAMS | Shift Management | SMGT-026 | SMGT-026 | SMGT-026 | Y |  | 3 | 2017-01-18 | 411680
CAMS | Shift Management | SMGT-028 | SMGT-028 | SMGT-028 | Y |  |  |  |  | Cannot Automate | We have to verify the result next day.
CAMS | Shift Management |  | SMGT-021 |  | Y | Harish | 3 | 2017-01-13 | 2017-01-17 | Assigned
CAMS | Shift Management | SMGT-004 |  | SMGT-004 |  | Harish | 1 | 2017-01-12 | 2017-01-12 | In-Progress
CAMS | Shift Management | SMGT-006 |  | SMGT-006 |  | Harish | 0 | 2017-01-12 | 2017-01-12 | Completed
WEB | Web Account Maintenance |  | ACMW-116 |  | Y
WEB | Web Account Maintenance |  | ACMW-134 |  | Y
WEB | Web Account Maintenance |  | ACMW-156 |  | Y
WEB | Web Account Maintenance |  | ACMW-167 |  | Y
WEB | Web Account Maintenance |  | ACMW-168 |  | Y
WEB | Web Account Maintenance |  | ACMW-183 |  | Y
WEB | Web Account Maintenance |  | ACMW-189 |  | Y
WEB | Web Account Maintenance |  | ACMW-214 |  | Y
WEB | Web Account Maintenance |  | ACMW-216 |  | Y
WEB | Web Account Maintenance |  | ACMW-219 |  | Y
WEB | Web Account Maintenance |  | ACMW-227 |  | Y
WEB | Web Account Maintenance |  | ACMW-231 |  | Y
WEB | Web Account Maintenance |  | ACMW-048 |  | Y
WEB | Web Account Maintenance |  | ACMW-052 |  | Y
WEB | Web Account Maintenance |  | ACMW-054 |  | Y
WEB | Web Account Maintenance |  | ACMW-084 |  | Y
WEB | Web Account Maintenance |  | ACMW-085 |  | Y
WEB | Web Account Maintenance |  | ACMW-074 |  | Y
WEB | Web Account Maintenance |  | ACMW-082 |  | Y
WEB | Web Account Maintenance |  | ACMW-262 |  | Y
WEB | Web Account Maintenance |  | ACMW-264 |  | Y
WEB | Web Account Maintenance |  | ACMW-265 |  | Y
WEB | Web Account Maintenance |  | ACMW-154 |  | Y
WEB | Web Account Maintenance |  | ACMW-269 |  | Y
WEB | Web Postpaid Account |  | PPACW-001 |  | Y
WEB | Web Postpaid Account |  | PPACW-003 |  | Y
WEB | Web Postpaid Account |  | PPACW-005 |  | Y
WEB | Web Postpaid Account |  | PPACW-011 |  | Y
WEB | Web Postpaid Account |  | PPACW-014 |  | Y
WEB | Web Postpaid Account |  | PPACW-018 |  | Y
WEB | Web Postpaid Account |  | PPACW-023 |  | Y
WEB | Web Postpaid Account |  | PPACW-010 |  | Y
CAMS | Account Establishment-CRM |  | ACEO-001 | ACEO-001 | Y |  |  |  |  | Pending Execution |  | Baycommuter annual pass discount plan not available.
CAMS | Account Establishment-CRM |  | ACEO-003 |  | Y | Laxmi | 2 | 2016-12-27 | 2016-12-28 | Completed | 2017-01-03
CAMS | Account Establishment-CRM | ACEO-008 | ACEO-008 |  | Y | Laxmi | 1 | 2016-12-29 | 2016-12-29 | Completed | 2017-01-03
CAMS | Account Establishment-CRM | ACEO-011 | ACEO-011 |  | Y | Laxmi | 0 | 2016-12-29 | 2016-12-29 | Completed | 2017-01-03
CAMS | Account Establishment-CRM |  | ACEO-012 | ACEO-012 | Y | Laxmi | 0 | 2016-12-29 | 2016-12-29 | Completed | 2017-01-03
CAMS | Account Establishment-CRM | ACEO-014 | ACEO-014 | ACEO-014 | Y | Laxmi | 1 | 2016-12-30 | 2016-12-30 | Completed | 2017-01-03
CAMS | Account Establishment-CRM |  | ACEO-020 |  | Y | Laxmi | 0 | 2016-12-30 | 2016-12-30 | Completed | 2017-01-03
CAMS | Account Establishment-CRM |  | ACEO-034 | ACEO-034 | Y | Laxmi | 0 | 2016-12-30 | 2016-12-30 | Completed | 2017-01-03
CAMS | Account Establishment-CRM |  | ACEO-045 |  | Y | Boopathi | 2 | 2017-01-24 | 2017-01-25 | Assigned |  | 7 days before account should be updated with payment. 12-01-2017: Assinged to boopathi.
CAMS | Account Establishment-CRM |  | ACEO-068 | ACEO-068 | Y | Laxmi | 1 | 2017-01-02 | 2017-01-02 | Completed | 2017-01-03
CAMS | Account Establishment-CRM | ACEO-081 | ACEO-081 |  | Y | Laxmi | 0 | 2017-01-02 | 2017-01-02 | Completed | 2017-01-03
CAMS | Account Establishment-CRM |  | ACEO-084 | ACEO-084 | Y | Laxmi | 0 | 2017-01-02 | 2017-01-02 | Completed | 2017-01-03
CAMS | Account Establishment-CRM |  | ACEO-086 | ACEO-086 | Y | Laxmi | 1 | 2017-01-03 | 2017-01-03 | Completed | 2017-01-03
CAMS | Account Establishment-CRM |  | ACEO-092 | ACEO-092 | Y | Laxmi | 0 | 2017-01-03 | 2017-01-03 | Completed | 2017-01-03
CAMS | Account Establishment-CRM | ACEO-007 |  | ACEO-007 | Y | Boopathi | 6 | 2016-12-27 | 2017-01-03 | Completed | 2017-01-03 | During this time, he worked on MOM. And analyze the test cases.
CAMS | Account Establishment-CRM | ACEO-017 |  | ACEO-017 | Y | Boopathi | 0 | 2016-12-27 | 2017-01-03 | Completed | 2017-01-04
CAMS | Account Establishment-CRM | ACEO-055 |  |  | Y | Boopathi | 0 | 2016-12-27 | 2017-01-03 | Completed | 2017-01-04
CAMS | Account Establishment-CRM | ACEO-076 |  |  | Y | Boopathi | 0 | 2016-12-27 | 2017-01-03 | Completed | 2017-01-04
CAMS | Account Establishment-CRM | ACEO-093 |  |  | Y | Boopathi | 0 | 2016-12-27 | 2017-01-03 | Completed | 2017-01-04
CAMS | Account Establishment-CRM |  |  | ACEO-002 | Y | Boopathi | 1 | 2017-01-27 | 2017-01-27 | Assigned |  | For the account "Bayway Residents Annual discount plan". 12-01-2017: Assigned to Boopathi
CAMS | Account Establishment-CRM |  |  | ACEO-030 | Y |  |  |  |  | Deferred |  | This will be automated with Display Checklist procedure
CAMS | Account Establishment-CRM |  |  | ACEO-038 | Y | Boopathi | 2 | 2017-01-30 | 2017-01-31 | Planned |  | Create private account with existing plate number of RCSP pre account. 12-01-2017: Assigned to Boopathi
CAMS | Account Establishment-CRM |  |  | ACEO-046 | Y | Boopathi | 1 | 2017-02-01 | 2017-02-01 | Planned |  | Payment not done after 7 days of opening the account; account status is PENDING-PAY. 12-01-2017: Assigned to Boopathi
CAMS | Account Establishment-CRM |  |  | ACEO-047 | Y | Boopathi | 0 | 2017-02-01 | 2017-02-01 | Planned |  | Payment done before 14 days of opening the account; account status is PENDING-PAY.
CAMS | Account Establishment-CRM |  |  | ACEO-048 | Y | Boopathi | 0 | 2017-02-01 | 2017-02-01 | Planned |  | Payment not done after 14 days of opening the account; account status is PENDING-PAY. 12-01-2017: Assigned to Boopathi
CAMS | Account Establishment-CRM |  |  | ACEO-053 | Y |  |  |  |  | Pending Execution |  | Baycommuter annual pass discount plan not available.
CAMS | Account Establishment-CRM |  |  | ACEO-059 | Y | Boopathi | 4 | 2017-01-03 | 2017-01-06 | Completed | 2017-01-10
CAMS | Account Establishment-CRM |  |  | ACEO-078 | Y | Boopathi | 0 | 2017-01-03 | 2017-01-06 | Completed | 2017-01-10
CAMS | Account Establishment-CRM |  |  | ACEO-082 | Y | Boopathi | 0 | 2017-01-03 | 2017-01-06 | Completed | 2017-01-10
CAMS | Account Establishment-CRM |  |  | ACEO-088 | Y | Boopathi | 0 | 2017-01-03 | 2017-01-06 | Completed | 2017-01-10
CAMS | Account Establishment-CRM |  |  | ACEO-137 | Y |  | 0 |  |  | Pending Execution |  | Prepaid Private account creation when Credit Card information associated to another account; Cancel the warning; enter new credit card info.
CAMS | Account Establishment-CRM |  |  | ACEO-153 | Y | Boopathi | 0 | 2017-01-03 | 2017-01-06 | Completed | 2017-01-10
CAMS | Account Establishment-CRM |  |  | ACEO-155 | Y | Boopathi | 0 | 2017-01-03 | 2017-01-06 | Completed | 2017-01-10
CAMS | Account Establishment-CRM |  |  | ACEO-165 | Y | Boopathi | 0 | 2017-01-03 | 2017-01-06 | Completed | 2017-01-10
CAMS | Account Establishment-CRM |  |  | ACEO-169 | [7 empty] | Wave 6
CAMS | Account Establishment-CRM |  |  | ACEO-173 | [7 empty] | Wave 6
DIMS | Inventory_Warranty_RMA_Program |  | RMA-008 |  | Y |  | 0.5 | 20-01-2017 | 20-01-2017 | In-Progress
DIMS | Inventory_Warranty_RMA_Program |  | RMA-014 |  | Y |  |  |  |  | In-Progress |  | Dependancy with Web Account creation
DIMS | Inventory_Warranty_RMA_Program |  | RMA-067 | RMA-067 | Y |  | 2 | 26-01-2017 | 28-01-2017 | In-Progress
DIMS | Inventory_Warranty_RMA_Program |  | RMA-024 |  | Y |  | 1.5 | 24-01-2017 | 25-01-2017 | In-Progress
DIMS | Inventory_Warranty_RMA_Program |  | RMA-035 |  | Y |  | 0.5 | 24-01-2017 | 24-01-2017 | In-Progress
DIMS | Inventory_Warranty_RMA_Program |  | RMA-045 |  | Y |  | 0.5 | 25-01-2017 | 25-01-2017 | In-Progress
DIMS | Inventory_Warranty_RMA_Program |  | RMA-048 |  | Y |  | 1 | 25-01-2017 | 26-01-2017 | In-Progress
DIMS | Inventory_Warranty_RMA_Program | RMA-005 |  | RMA-005 |  |  | 1.5 | 19-01-2017 | 20-01-2017 | In-Progress
DIMS | Inventory_Warranty_RMA_Program |  |  | RMA-006 |  |  | o.5 | 23-01-2017 | 23-01-2017 | In-Progress
DIMS | Inventory_Warranty_RMA_Program |  |  | RMA-007 |  |  | o.5 | 23-01-2017 | 23-01-2017 | In-Progress
TPMS | Transponder and Plate_Status |  | TNPST-001 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-002 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-005 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-006 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-009 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-010 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-014 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-021 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-023 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-024 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-063 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-067 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-069 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-074 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-075 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-077 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-081 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-088 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-089 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-094 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-099 |  | N
TPMS | Transponder and Plate_Status |  | TNPST-103 |  | N
FPMS | Money_Service_Provider |  | MOSP-001 |  | ?
FPMS | Money_Service_Provider |  | MOSP-006 |  | ?
FPMS | Money_Service_Provider |  | MOSP-011 |  | ?
FPMS | Money_Service_Provider |  | MOSP-012 |  | ?
FPMS | Money_Service_Provider |  | MOSP-013 |  | ?
FPMS | Money_Service_Provider |  | MOSP-021 |  | ?
VEMS | Invoice_Generation_Escalation |  | INVE-001 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-010 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-005 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-006 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-007 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-008 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-015 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-019 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-027 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-047 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-049 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-065 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-068 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-072 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-076 |  | N
VEMS | Invoice_Generation_Escalation |  | INVE-080 |  | N
VEMS | Court_Processing |  | CTPROC-001 |  | N
VEMS | Court_Processing |  | CTPROC-004 |  | N
VEMS | Court_Processing |  | CTPROC-005 |  | N
VEMS | Court_Processing |  | CTPROC-010 |  | N
VEMS | Court_Processing |  | CTPROC-011 |  | N
VEMS | Court_Processing |  | CTPROC-017 |  | N
ADMIN | Internal Control |  | INTC - 001 |  | Y
ADMIN | Internal Control |  | INTC -058 |  | Y
ADMIN | Internal Control |  | INTC -052 |  | Y
ADMIN | Internal Control |  | INTC -065 |  | Y
ADMIN | Internal Control |  | INTC - 023 |  | Y
ADMIN | Internal Control |  | INTC - 023 |  | Y
CAMS | Account Merging | ACMG-001 | ACMG-001 |  | Y | Harish | 4 | 2017-01-23 | 2017-01-27 | Assigned |  | No Regression Test Cases | Ds Divya, Kumar suseeran
CAMS | Account Merging |  | ACMG-002 |  | Y | Harish | 1 | 2017-01-30 | 2017-01-30 | Assigned
CAMS | Account Merging | ACMG-006 | ACMG-006 |  | Y | Harish | 0 | 2017-01-30 | 2017-01-30 | Assigned
CAMS | Account Merging |  | ACMG-009 |  | Y | Harish | 2 | 2017-01-31 | 2017-02-01 | Assigned
CAMS | Account Merging | ACMG-011 | ACMG-011 |  | Y | Harish | 1 | 2017-02-02 | 2017-02-02 | Assigned
CAMS | Account Conversion |  | ACNV-001 |  | Y |  |  |  |  | Can't able to test now. May be future waves, this functionaltiy will be available.(As per manual tester)
CAMS | Account Conversion |  | ACNV-004 |  | Y
CAMS | Account Linking | ACLK-001 | ACLK-001 |  | Y | Bharath | 4 | 2017-01-16 | 2017-01-19 | Assigned |  | No Regression Test cases | Aman Jain
CAMS | Account Linking | ACLK-002 | ACLK-002 |  | Y | Bharath | 1 | 2017-01-20 | 2017-01-20 | Assigned
CAMS | Account Linking | ACLK-014 | ACLK-014 |  | Y | Bharath | 3 | 2017-01-23 | 2017-01-25 | Assigned
CAMS | Account Linking | ACLK-019 | ACLK-019 |  | Y | Bharath | 1 | 2017-01-27 | 2017-01-27 | Assigned
CAMS | Account Linking | ACLK-033 | ACLK-033 |  | Y | Bharath | 3 | 2017-01-30 | 2017-02-01 | Assigned
CAMS | Account Linking |  | ACLK-034 |  | Y | Bharath | 4 | 2017-02-02 | 2017-02-07 | Assigned
CAMS | CRM_Account_Inactivity_Closure |  | ACICL-001 |  | Y
CAMS | CRM_Account_Inactivity_Closure |  | ACICL-002 |  | Y
CAMS | CRM_Account_Inactivity_Closure |  | ACICL-006 |  | Y
CAMS | CRM_Account_Inactivity_Closure |  | ACICL-010 |  | Y
CAMS | CRM_Account_Inactivity_Closure |  | ACICL-011 |  | Y
CAMS | CRM_Account_Inactivity_Closure |  | ACICL-018 |  | Y
CAMS | CRM_Account_Inactivity_Closure |  | ACICL-022 |  | Y
CAMS | CRM_Account_Inactivity_Closure |  | ACICL-026 |  | Y
CAMS | Bankruptcy Deceased |  | BRDC-001 |  | Y
CAMS | Bankruptcy Deceased |  | BRDC-004 |  | Y
CAMS | Bankruptcy Deceased |  | BRDC-013 |  | Y
CAMS | Bankruptcy Deceased |  | BRDC-015 |  | Y
CAMS | Bankruptcy Deceased |  | BRDC-021 |  | Y
CAMS | Bankruptcy Deceased |  | BRDC-026 |  | Y
CAMS | Payment Processing | PMTP-001 | PMTP-001 |  | Y | Laxmi | 2 | 2017-01-16 | 2017-01-17 | Assigned
CAMS | Payment Processing |  | PMTP-002 |  | Y | Laxmi | 1 | 2017-01-18 | 2017-01-18 | Assigned
CAMS | Payment Processing |  | PMTP-003 |  | Y | Laxmi | 1 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | Payment Processing |  | PMTP-005 |  | Y | Laxmi | 0 | 2017-01-19 | 2017-01-19 | Assigned
CAMS | Payment Processing |  | PMTP-012 |  | Y | Laxmi | 2 | 2017-01-20 | 2017-01-23 | Assigned
CAMS | Payment Processing | PMTP-027 | PMTP-027 |  | Y | Laxmi | 4 | 2017-01-24 | 2017-01-27 | Assigned
CAMS | Payment Processing |  | PMTP-065 |  | Y | Laxmi | 1 | 2017-01-30 | 2017-01-30 | Assigned
CAMS | Payment Processing |  | PMTP-030 |  | Y | Laxmi | 1 | 2017-01-31 | 2017-01-31 | Assigned
CAMS | Payment Processing |  | PMTP-034 |  | Y | Laxmi | 1 | 2017-02-01 | 2017-02-01 | Assigned
CAMS | Payment Processing |  | PMTP-035 |  | Y | Laxmi | 0 | 2017-02-01 | 2017-02-01 | Assigned
CAMS | Payment Processing |  | PMTP-040 |  | Y | Laxmi | 1 | 2017-02-02 | 2017-02-02 | Assigned
CAMS | Payment Processing | PMTP-046 | PMTP-046 |  | Y | Nishanth | 2 | 2017-01-16 | 2017-01-17 | Assigned
CAMS | Payment Processing | PMTP-047 | PMTP-047 |  | Y | Nishanth | 2 | 2017-01-18 | 2017-01-19 | Assigned
CAMS | Payment Processing |  | PMTP-048 |  | Y | Nishanth | 2 | 2017-01-20 | 2017-01-23 | Assigned
CAMS | Payment Processing | PMTP-055 | PMTP-055 |  | Y | Nishanth | 4 | 2017-01-24 | 2017-01-27 | Assigned
CAMS | Payment Processing |  | PMTP-078 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing |  | PMTP-079 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing |  | PMTP-081 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing |  | PMTP-082 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing |  | PMTP-083 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing |  | PMTP-086 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing |  | PMTP-087 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing |  | PMTP-090 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing |  | PMTP-092 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing |  | PMTP-093 |  | Y |  |  |  |  | blocked in jama
CAMS | Payment Processing | PMTP-013 |  |  |  | Laxmi |  | 2017-02-03 | 2017-02-03 | Assigned
CAMS | Payment Processing | PMTP-019 |  |  |  | Laxmi |  | 2017-02-03 | 2017-02-03 | Assigned
ADMIN | Customer Survey |  | CUSV-001 |  | Y
ADMIN | Customer Survey |  | CUSV-002 |  | Y
ADMIN | Customer Survey |  | CUSV-006 |  | Y
ADMIN | Customer Survey |  | CUSV-008 |  | Y